Stag’d

Implementation Plan

V1 · Chameleon Ideas · April 2026

Team-ready build reference · Confidential

This document is the single source of truth for the Stag’d V1 build. Every product decision referenced here has been deliberated and locked. Changes require sign-off from the Director of Operations before implementation.

# 1.  Team Structure

Four people build V1. Every feature in this document is assigned to a primary owner. Ownership means accountable for delivery — not necessarily working alone.

| Role | Handle | Primary responsibility | Stack ownership |
| --- | --- | --- | --- |
| UI/UX Consultant | UI/UX | Design system, all screens, component specs, Figma handoff | Figma, design tokens, animation specs |
| Frontend Dev 1 | FE1 | Mobile app (React Native / Expo), all app screens | Expo, React Native, Supabase client |
| Frontend Dev 2 | FE2 | Web profiles (Next.js), shared component library | Next.js, Vercel, SEO, shared UI components |
| Backend Developer | BE | Node/Express API, Supabase schema, integrations, VPS | Node.js, Supabase, Safepay, QRfy, Socket.io |

# 2.  Technology Stack

| Mobile App | React Native · Expo |
| --- | --- |

| Framework | React Native with Expo SDK — single codebase for iOS and Android |
| --- | --- |
| Language | TypeScript throughout — no plain JavaScript in any file |
| Navigation | Expo Router (file-based routing, matches Next.js conventions) |
| State | Zustand for global state, React Query for server state and caching |
| Styling | StyleSheet API + custom design token system from Figma brief |
| Camera / QR | expo-camera for scanner mode — no third-party scanner library |
| Push notifs | Expo Push Notifications + OneSignal for marketing layer |
| Media | expo-image for optimised image loading, expo-av for video reels |

| Web Profiles | Next.js · Vercel |
| --- | --- |

| Framework | Next.js 14 with App Router — server components for SEO |
| --- | --- |
| Rendering | Static generation for artist profiles — revalidates on profile update |
| Hosting | Vercel — zero config, instant deploys on push to main |
| SEO | Artist name + discipline + city in page title and meta on every profile |
| Shared UI | Component library shared with mobile where logic allows |

| Backend API | Node.js · Express · Hostinger VPS |
| --- | --- |

| Runtime | Node.js 20 LTS |
| --- | --- |
| Framework | Express with structured route → controller → service pattern |
| Real-time | Socket.io for commission chat and live door dashboard |
| Process manager | PM2 — keeps Node running 24/7, restarts on crash |
| Reverse proxy | Nginx — routes traffic, handles HTTPS termination |
| SSL | Certbot (Let’s Encrypt) — free, auto-renewing certificates |
| Deployment | GitHub Actions — auto-deploy to VPS on push to main branch |
| Logging | Winston for structured logs, Morgan for HTTP request logging |

| Database, Auth, Storage | Supabase · PostgreSQL |
| --- | --- |

| Database | PostgreSQL via Supabase — fully relational, clean foreign keys |
| --- | --- |
| Auth | Supabase Auth — phone OTP, email, social login (Instagram OAuth) |
| Storage | Supabase Storage — portfolio images, event covers, payment screenshots |
| Real-time | Supabase Realtime — live door dashboard subscriptions |
| Row-level sec. | RLS policies on all tables — users only access their own data |
| Migrations | Supabase CLI — all schema changes version-controlled in /supabase/migrations |

| Third-Party Integrations |  |
| --- | --- |

| Payments | Safepay — JazzCash, Easypaisa, card in one API. Per-transaction fee, no monthly cost. |
| --- | --- |
| QR generation | QRfy API — branded dynamic QRs. Single-use invalidation handled on Stag’d backend. |
| CDN | Cloudflare — media delivery, free tier covers V1 entirely |
| Email | Resend — transactional email (ticket confirmation, payment receipts, agreement email) |
| Maps | Google Maps Embed API — optional venue map on event page |
| Instagram | Instagram Basic Display API — OAuth portfolio import for artists |

All infrastructure runs free-tier until real users exist. First paid upgrade is Railway → Hostinger VPS before launch (~$8/mo). Total infrastructure cost at launch: under PKR 15,000/month.

# 3.  Database Schema

All tables live in Supabase PostgreSQL. Row-level security is enabled on every table. Migrations are written and applied via Supabase CLI — never edited directly in the dashboard.

users

| Column | Type | Constraint | Description |
| --- | --- | --- | --- |
| id | uuid | PK | Supabase Auth UID — same across all tables |
| phone | text | UNIQUE | Primary login identifier |
| email | text | UNIQUE | Optional — for notifications and ticket receipts |
| full_name | text | NOT NULL | Display name across all surfaces |
| username | text | UNIQUE | stagd.app/username URL slug |
| role | text | NOT NULL | creative ¦ general ¦ both |
| city | text |  | Karachi ¦ Lahore ¦ Islamabad |
| avatar_url | text |  | Supabase Storage URL |
| created_at | timestamptz | NOT NULL | Auto-set on insert |

artist_profiles

| Column | Type | Constraint | Description |
| --- | --- | --- | --- |
| id | uuid | PK FK | References users.id |
| bio | text |  | 150 char max, enforced at API layer |
| disciplines | text[] |  | Array of discipline tags |
| availability | text |  | available ¦ busy ¦ unavailable |
| starting_rate | integer |  | PKR, null if rates_on_request |
| rates_on_request | boolean |  | Shows ‘Rates on request’ instead of rate |
| travel_available | boolean |  | Willing to travel for projects |
| accent_color | text |  | Hex — artist-chosen tint for web profile |
| instagram_handle | text |  | For OAuth portfolio import |
| verified | boolean |  | Manual verification by Stag’d team |

portfolio_items

| Column | Type | Constraint | Description |
| --- | --- | --- | --- |
| id | uuid | PK |  |
| artist_id | uuid | FK | References users.id |
| image_url | text | NOT NULL | Supabase Storage URL |
| title | text |  | Optional caption |
| is_hidden | boolean |  | Hidden from public but not deleted |
| sort_order | integer |  | Artist-controlled display order |
| created_at | timestamptz | NOT NULL |  |

past_projects

| Column | Type | Constraint | Description |
| --- | --- | --- | --- |
| id | uuid | PK |  |
| artist_id | uuid | FK | References users.id |
| title | text | NOT NULL |  |
| description | text |  |  |
| image_url | text |  |  |
| value_range | text |  | e.g. PKR 50k–80k, manually entered |
| created_at | timestamptz | NOT NULL |  |

events

| Column | Type | Constraint | Description |
| --- | --- | --- | --- |
| id | uuid | PK |  |
| organiser_id | uuid | FK | References users.id |
| title | text | NOT NULL |  |
| description | text |  |  |
| event_type | text |  | concert ¦ workshop ¦ gallery ¦ spoken_word ¦ other |
| cover_image_url | text |  |  |
| venue_name | text |  |  |
| venue_address | text |  |  |
| city | text |  |  |
| maps_pin | text |  | Google Maps URL, optional |
| starts_at | timestamptz | NOT NULL |  |
| doors_at | timestamptz |  |  |
| is_recurring | boolean |  |  |
| status | text |  | draft ¦ live ¦ cancelled ¦ completed |
| created_at | timestamptz | NOT NULL |  |

ticket_tiers

| Column | Type | Constraint | Description |
| --- | --- | --- | --- |
| id | uuid | PK |  |
| event_id | uuid | FK | References events.id |
| name | text | NOT NULL | e.g. General Admission, VIP, Door |
| price | integer | NOT NULL | PKR, 0 for free events |
| capacity | integer | NOT NULL | Total tickets in this tier |
| is_door_only | boolean |  | Not purchasable online — door staff only |
| sort_order | integer |  | Display order in tier list |

tickets

| Column | Type | Constraint | Description |
| --- | --- | --- | --- |
| id | uuid | PK |  |
| ticket_id | text | UNIQUE | TKT-YYYY-XXXXX display format |
| event_id | uuid | FK | References events.id |
| tier_id | uuid | FK | References ticket_tiers.id |
| buyer_id | uuid | FK | References users.id, null for guest |
| buyer_name | text | NOT NULL | Stored separately for guest checkout |
| buyer_email | text | NOT NULL |  |
| quantity | integer | NOT NULL |  |
| total_paid | integer | NOT NULL | PKR |
| qr_url | text |  | QRfy-generated QR image URL |
| scanned_at | timestamptz |  | Null until scanned. Set on first scan. |
| purchased_at | timestamptz | NOT NULL |  |

commissions

| Column | Type | Constraint | Description |
| --- | --- | --- | --- |
| id | uuid | PK |  |
| client_id | uuid | FK | References users.id |
| artist_id | uuid | FK | References users.id |
| status | text | NOT NULL | enquiry ¦ in_discussion ¦ in_progress ¦ completed ¦ cancelled |
| brief_what | text |  | Client’s initial brief — what they need |
| brief_budget | text |  | Budget range or slider value |
| brief_timeline | text |  | Timeline chip selection |
| brief_reference | text |  | Supabase Storage URL for reference image |
| created_at | timestamptz | NOT NULL |  |

proposals

| Column | Type | Constraint | Description |
| --- | --- | --- | --- |
| id | uuid | PK |  |
| commission_id | uuid | FK | References commissions.id |
| title | text | NOT NULL |  |
| description | text |  |  |
| total_price | integer | NOT NULL | PKR |
| deposit_amount | integer |  | PKR, defaults to 50% of total |
| delivery_date | date |  |  |
| revisions | integer |  | Number of revisions included |
| deliverables | text |  | ‘What you’ll get’ free text |
| status | text | NOT NULL | pending ¦ accepted ¦ tweaking ¦ superseded |
| created_at | timestamptz | NOT NULL |  |

payment_confirmations

| Column | Type | Constraint | Description |
| --- | --- | --- | --- |
| id | uuid | PK |  |
| commission_id | uuid | FK | References commissions.id |
| type | text | NOT NULL | deposit ¦ balance |
| amount | integer | NOT NULL | PKR |
| client_marked_at | timestamptz |  | When client tapped Mark as Paid |
| screenshot_url | text |  | Optional Supabase Storage URL |
| artist_confirmed_at | timestamptz |  | When artist tapped Confirm Receipt |

messages

| Column | Type | Constraint | Description |
| --- | --- | --- | --- |
| id | uuid | PK |  |
| commission_id | uuid | FK | References commissions.id |
| sender_id | uuid | FK | References users.id |
| type | text | NOT NULL | text ¦ proposal ¦ payment_confirmation ¦ status_update |
| body | text |  | Text content, null for non-text types |
| ref_id | uuid |  | Reference to proposal or payment_confirmation id |
| created_at | timestamptz | NOT NULL |  |

reviews

| Column | Type | Constraint | Description |
| --- | --- | --- | --- |
| id | uuid | PK |  |
| commission_id | uuid | FK | References commissions.id |
| reviewer_id | uuid | FK | References users.id |
| reviewee_id | uuid | FK | References users.id |
| rating | integer | NOT NULL | 1–5 |
| body | text |  | 150 char max |
| created_at | timestamptz | NOT NULL |  |

door_staff

| Column | Type | Constraint | Description |
| --- | --- | --- | --- |
| id | uuid | PK |  |
| event_id | uuid | FK | References events.id |
| user_id | uuid | FK | References users.id, null if phone-only |
| phone | text |  | For non-account door staff |
| scanner_token | text |  | One-time token for SMS scanner link |

# 4.  API Surface

All endpoints are prefixed with /api/v1. Authentication uses Supabase JWT passed in the Authorization header. Public endpoints require no token.

### Auth

| Method | Endpoint | Auth | Description |
| --- | --- | --- | --- |
| POST | /auth/otp/request | Public | Send OTP to phone number |
| POST | /auth/otp/verify | Public | Verify OTP, return session token |
| POST | /auth/instagram | Authenticated | Instagram OAuth callback, import portfolio |
| DELETE | /auth/session | Authenticated | Sign out, invalidate session |

### Users & Profiles

| Method | Endpoint | Auth | Description |
| --- | --- | --- | --- |
| GET | /users/:username | Public | Get public artist profile by username |
| PATCH | /users/me | Authenticated | Update own profile fields |
| POST | /users/me/portfolio | Authenticated | Upload a portfolio item |
| PATCH | /users/me/portfolio/:id | Authenticated | Reorder, hide, or update a portfolio item |
| DELETE | /users/me/portfolio/:id | Authenticated | Delete a portfolio item |
| POST | /users/me/past-projects | Authenticated | Add a past project (cold start) |
| GET | /users/me/dashboard | Authenticated | Artist dashboard stats and active projects |

### Events

| Method | Endpoint | Auth | Description |
| --- | --- | --- | --- |
| GET | /events | Public | List events with filters (city, type, date, price) |
| GET | /events/:id | Public | Single event detail page |
| POST | /events | Authenticated | Create a new event |
| PATCH | /events/:id | Authenticated | Update event details (organiser only) |
| DELETE | /events/:id | Authenticated | Cancel event |
| POST | /events/:id/door-staff | Authenticated | Assign door staff by phone or username |

### Tickets

| Method | Endpoint | Auth | Description |
| --- | --- | --- | --- |
| GET | /events/:id/tickets | Authenticated | Get ticket tiers and availability |
| POST | /events/:id/tickets/purchase | Public | Purchase ticket (guest or authenticated) |
| GET | /tickets/:ticketId | Authenticated | Get ticket detail (buyer only) |
| GET | /verify/:ticketId | Public | QR verification endpoint — single-use invalidation |
| POST | /events/:id/walkin | Authenticated | Issue walk-in ticket (door staff only) |
| GET | /events/:id/live | Authenticated | Live door dashboard — scan count by tier |

### Commissions

| Method | Endpoint | Auth | Description |
| --- | --- | --- | --- |
| POST | /commissions | Authenticated | Send an enquiry (brief form submission) |
| GET | /commissions | Authenticated | List own commissions (client or artist view) |
| GET | /commissions/:id | Authenticated | Single commission thread |
| PATCH | /commissions/:id/status | Authenticated | Update status (either party) |
| POST | /commissions/:id/proposals | Authenticated | Send a proposal (artist only) |
| PATCH | /commissions/:id/proposals/:pid | Authenticated | Accept or mark for tweaking (client only) |
| POST | /commissions/:id/messages | Authenticated | Send a message in the thread |
| POST | /commissions/:id/payment | Authenticated | Mark payment sent or confirm receipt |
| POST | /commissions/:id/review | Authenticated | Submit a review (post-completion only) |

### Explore & Search

| Method | Endpoint | Auth | Description |
| --- | --- | --- | --- |
| GET | /search/artists | Public | Search artists by discipline, city, availability |
| GET | /search/events | Public | Search events by type, city, date, price |
| GET | /home | Authenticated | Home feed — events soon, featured, following |

# 5.  Build Phases

| Phase 0 — Founder Scaffold | Weeks 1–2 · Founder + Claude Code |
| --- | --- |

This phase is completed by the Director of Operations using Claude Code before handing to the development team. The output is a working skeleton — not a finished product.

Exit criteria: user can sign up with phone OTP, profile is created in the database, and a single API endpoint returns data to the app. All four projects are version-controlled on GitHub.

| Feature | Notes | Owner | Priority |
| --- | --- | --- | --- |
| Supabase project + full schema | All tables, RLS policies, migrations written | Founder | P0 |
| GitHub repos (3) | stagd-app, stagd-web, stagd-api — private, branching convention set | Founder | P0 |
| Node/Express boilerplate | Folder structure, middleware, route pattern, env config | Founder | P0 |
| Expo app initialised | TypeScript, Expo Router, Supabase client connected | Founder | P0 |
| Next.js project initialised | App Router, Supabase client, Vercel connected | Founder | P0 |
| Phone OTP auth end-to-end | Request OTP → verify → session → profile created in DB | Founder | P0 |
| VPS configured | Nginx, PM2, Certbot, GitHub Actions deploy pipeline | Founder | P0 |
| Design token system | Figma brief colours, typography, spacing as code constants | UI/UX | P0 |

| Phase 1 — Core Product | Weeks 3–10 · Full Team |
| --- | --- |

Everything a user needs to onboard, discover, hire, and attend an event. No payments in V1 commissions. Ticketing payments live from day one.

### Onboarding

| Feature | Notes | Owner | Priority |
| --- | --- | --- | --- |
| Creative onboarding flow | 6 steps as per Figma brief | FE1 | P0 |
| General user onboarding | 5 steps, interest tags, city | FE1 | P0 |
| Artist profile publish | Preview + publish, stagd.app/username live | FE1+BE | P0 |
| Past projects (cold start) | Manual add at onboarding — title, desc, image, value range | FE1+BE | P1 |
| Instagram OAuth import | User selects own posts to import as portfolio items | BE | P1 |

### Discovery

| Feature | Notes | Owner | Priority |
| --- | --- | --- | --- |
| Home screen | Events soon, browse by discipline, featured creatives, following feed | FE1+BE | P0 |
| Artist profile page | Full profile, portfolio grid, tabs, web version | FE1+FE2 | P0 |
| Event listing page | Hero, details, persistent CTA bar | FE1 | P0 |
| Explore / search | Artists tab + Events tab with filters | FE1+BE | P0 |
| City selector | Affects all home content | FE1 | P0 |
| SEO — web profiles | Artist name + discipline + city in meta, server-side rendered | FE2 | P0 |
| Following system | Follow artist, following feed on home | FE1+BE | P1 |

### Ticketing

| Feature | Notes | Owner | Priority |
| --- | --- | --- | --- |
| Event creation flow | 5 steps, ticket tiers, free event toggle, recurring prompt | FE1+BE | P0 |
| Ticket purchase flow | Tier selection, quantity, Safepay payment, QR generation | FE1+BE | P0 |
| QRfy integration | API call on purchase, branded QR embedded in ticket card | BE | P0 |
| Ticket confirmation screen | Boarding pass UI, add to calendar, share | FE1 | P0 |
| Ticket email | Confirmation email via Resend immediately on purchase | BE | P0 |
| Scanner mode | Full-screen, camera, SCAN + SELL buttons, persistent banner | FE1+BE | P0 |
| QR verification endpoint | Single-use invalidation, green/red screen, buyer name shown | BE | P0 |
| Door staff assignment | Organiser assigns by username or phone, SMS token for non-users | FE1+BE | P0 |
| Walk-in ticket issuance | SELL TICKET flow in scanner mode, door allocation enforcement | FE1+BE | P0 |
| Live door dashboard | Real-time scan count by tier, Supabase Realtime subscription | FE1+BE | P0 |
| Poster QR generation | Static QR pointing to event listing page, separate from ticket QRs | BE | P1 |
| Guest checkout | Ticket purchase without account, email delivery only | FE1+BE | P1 |
| Payout model | 50/50 split, 48hr pre/post, first-event 100% post, Safepay payouts | BE | P0 |

### Commissions

| Feature | Notes | Owner | Priority |
| --- | --- | --- | --- |
| Hire Me button + brief form | 4 fields, budget slider PKR 5k–500k, disclaimer always visible | FE1+BE | P0 |
| Commission chat thread | Real-time via Socket.io, message types, project status bar | FE1+BE | P0 |
| Proposal card | Fixed price, deposit, balance, delivery date, revisions, deliverables | FE1+BE | P0 |
| Proposal actions | Sounds good / Let’s tweak it, revised proposals marked superseded | FE1+BE | P0 |
| Payment confirmation layer | Mark as paid, optional screenshot, artist confirms receipt | FE1+BE | P0 |
| Audit trail | Full timestamped payment log in thread, permanent | BE | P0 |
| Review system | Star + 150 char, both parties, gated on payment confirmation | FE1+BE | P1 |
| Review prompt | On completion — dismissable, accessible from project history permanently | FE1 | P1 |
| Inbox tabs | All / Active / Enquiries / Completed | FE1 | P0 |

### Artist Dashboard

| Feature | Notes | Owner | Priority |
| --- | --- | --- | --- |
| Stats grid | Profile views, enquiries, tickets sold, new followers | FE1+BE | P1 |
| Active projects card | Client, project type, due date, status | FE1 | P1 |
| Upcoming events card | Next event, tickets sold progress bar | FE1 | P1 |
| Time filter | This month / Last month / All time | FE1+BE | P1 |

| Phase 2 — Launch-Ready Polish | Weeks 11–14 · Full Team |
| --- | --- |

Performance, edge cases, and everything that makes the product feel finished rather than functional.

| Feature | Notes | Owner | Priority |
| --- | --- | --- | --- |
| Dark mode | Full app adapts to device theme, all components tested | FE1+FE2 | P1 |
| Offline fallback | Cached attendee list when VPS unreachable at door | BE | P1 |
| Push notification system | Commission updates, ticket confirmation, event reminders | FE1+BE | P1 |
| App Store + Play Store submission | Screenshots, descriptions, ASO keywords | UI/UX+FE1 | P0 |
| Image optimisation | Masonry grid performance, lazy loading, Cloudflare CDN | FE1+FE2 | P1 |
| Error states | Every screen has empty state, error state, loading state designed | UI/UX+FE1 | P1 |
| Accessibility | Minimum tap targets, contrast ratios, screen reader basics | UI/UX+FE1 | P2 |
| Analytics | Posthog or Mixpanel — event tracking for funnel and feature usage | BE | P1 |
| Rate limiting | API rate limiting on auth and purchase endpoints | BE | P0 |
| Security audit | SQL injection, XSS, auth token handling reviewed before launch | BE | P0 |

# 6.  Integration Build Order

Integrations are built in this sequence. Each one unblocks the next. Do not start an integration before the one above it is tested and working.

| 1. Supabase Auth | Phone OTP must work before anything else. Foundation of all user data. |
| --- | --- |
| 2. Supabase Storage | Portfolio images needed before profiles are testable end-to-end. |
| 3. QRfy API | QR generation needed before ticket purchase flow is testable. |
| 4. Safepay | Payment gateway. Integrate in test mode first, switch to live before launch. |
| 5. Resend | Transactional email. Ticket confirmations and organiser agreement emails. |
| 6. Socket.io | Commission chat real-time layer. Build after REST commission endpoints work. |
| 7. Supabase Realtime | Live door dashboard. Build after scanning endpoint is working. |
| 8. Instagram OAuth | Portfolio import. Nice-to-have for launch, not a blocker. |
| 9. Google Maps Embed | Venue map on event page. Public API, minimal integration work. |
| 10. OneSignal | Push notifications marketing layer. After core Expo push is working. |

# 7.  Team Conventions

### Git branching

| main | Production. Only merges from staging via pull request with review. |
| --- | --- |
| staging | Pre-launch testing. All features merge here first. |
| feature/* | One branch per feature. e.g. feature/proposal-card |
| fix/* | Bug fixes. e.g. fix/scanner-crash-on-iphone-12 |

### Commit message format

feat: add proposal card to commission thread

fix: scanner returning wrong result on second scan

chore: update Supabase client to v2.38

docs: add API endpoint for walk-in ticket issuance

### Environment files

- Never commit .env files to GitHub — .gitignore must include all .env* files from day one

- Maintain three environments: .env.local (dev), .env.staging, .env.production

- All environment variables documented in /docs/ENV.md in each repo — keys listed, values never

### Code review rules

- Every pull request requires one review before merge — no self-merges to staging or main

- BE reviews FE pull requests that touch API contracts — catch breaking changes before they merge

- UI/UX reviews any PR that touches a screen layout before it goes to staging

- No PR merges on a Friday without explicit sign-off from the Director of Operations

### Definition of done — per feature

- Feature works on iOS, Android, and web where applicable

- Empty state, error state, and loading state are all handled

- No hardcoded strings — all copy matches the locked spec

- API endpoint has basic rate limiting if it touches auth or payments

- UI/UX sign-off on any new screen before it goes to staging

# 8.  V1 Launch Checklist

Every item on this list must be ticked before the app goes to the App Store and Play Store. No exceptions.

### Product

- All P0 features complete and tested on real devices

- Organiser agreement signed by at least 3 Founding 50 event organisers

- At least one full ticketed event run through the platform on TestFlight/internal build

- Scanner mode tested at a real door with real attendees before launch night

- QR verification tested with screenshot-share attempt — second scan must fail

### Infrastructure

- VPS hardened — SSH key auth only, no password login, firewall configured

- Supabase backups enabled and tested — restore at least once before launch

- Safepay live credentials tested with a real PKR transaction

- Cloudflare CDN serving all media assets, not Supabase Storage direct URLs

- Rate limiting active on /auth and /tickets/purchase endpoints

- SSL certificate valid and auto-renewing via Certbot

### App Store

- iOS TestFlight build tested by at least 20 people including non-technical users

- Android APK tested on at least 3 different Android devices

- App Store screenshots in Stag’d visual language — no generic mockups

- App description leads with problem solved, not feature list

- Privacy policy live at stagd.app/privacy — required by both stores

- Terms of service live at stagd.app/terms

### Legal

- Stag’d entity registered with SECP or operating under Chameleon Ideas formally

- IPO Pakistan trademark application filed for Stag’d name and logo

- Organiser Agreement reviewed by a qualified Pakistani lawyer

- Safepay merchant agreement signed

The launch checklist is signed off by the Director of Operations. No individual team member has authority to declare V1 ready without this sign-off.

Stag’d  ·  stagd.app  ·  Implementation Plan V1  ·  Chameleon Ideas  ·  April 2026  ·  Confidential